## Product
ID | Name | Description | Sprint | Story points | Total for Sprint
1 | Page loading (design, map, location) | Just entering the page http://suzy.somee.com/ and its loading | Milestone 0.1 | 50 | 50
2 | Registration /sign-up | Adding new user or signing up existing user | Milestone 0.2 | 30 | 100
10 | Logout | Log out from the system
3 | Get user location | Get information about geo-location of any user that is present in the system DB |  | 20
12 | Make check-in at current position | User should make special activities to save his/her current location |  | 10
13 | Position correction by mouse (Drag the map-pointer) | If location of current user is misplaced by map-pointer, user change it by dragging the pointer with the help of mouse |  | 25
14 | Get location history of the user check-ins | Current user can see history (all saved locations) and statistics of all selected user's checkins and their counter |  | 15
4 | Pofile information | Editing personal information | Milestone 0.3 | 10 | 100
5 | Avatar | User can add-delete-change avatar |  | 15
6 | Follow | Add users to personal Followings list (page) |  | 10
7 | Unfollow | Delete user from personal Followings list
8 | Followers | See who is fillowing you |  | 10
9 | Followings on map | See all personal Followings on map |  | 25
16 | Followings list | User can observe all his ollowings. Following is a person that is followed by current user. |  | 10
15 | Error logger | Logging and saving to the file all errors, exceptions, warnings. During using the system this Logger element of system helps developers and Administrator to track errors and bugs to make the system better |  | 20
11 | Mobile version | Using system on mobile phone | Milestone 0.4 | 60 | 100
17 | Bugs fixing | Final testing |  | 40