## Sprint 1
ID | Name | Description | Sprint | Story points | Total for Sprint
1 | Page loading (design, map, location) | Just entering the page http://suzy.somee.com/ and its loading, map displaying, location request | Milestone 0.1 | 50 | 50
Task ID | Name | Description | Link | Story points
1 | DB selection | DB analysis and obtaining the best variant | https://github.com/exytab/Suzy/issues/3 | 5
2 | DB model | Decomposition of subject, DB instance creation, main tables modeling | https://github.com/exytab/Suzy/issues/1 | 15
3 | DB implementation | SQL script for DB model creation |  | 10
4 | Design templates (CSS, html, map,frameworks) | Choosing template for page design; studying the possebilities of the chosen variant | https://github.com/exytab/Suzy/issues/2 | 10
5 | Basic pages implementation | Simple html templates for future web-pages |  | 10

## Sprint 2
ID | Name | Description | Sprint | Story points | Total for Sprint
2 | Registration /sign-up | Adding new user or signing up existing user | Milestone 0.2 | 30 | 100
10 | Logout | Log out from the system
3 | Get user location | Get information about geo-location of any user that is present in the system DB |  | 20
12 | Make check-in at current position | User should make special activities to save his/her current location |  | 10
13 | Position correction by mouse (Drag the map-pointer) | If location of current user is misplaced by map-pointer, user change it by dragging the pointer with the help of mouse |  | 25
14 | Get location history of the user check-ins | Current user can see history (all saved locations) and statistics of all selected user's checkins and their counter |  | 15
ID.Task ID | Name | Description | Link | Story points
2.1. | Sign In / Sign Out | Session implementing. New pages for sign in users building. | https://github.com/exytab/Suzy/issues/19 | 10
10.1. | Sign In / Sign Out | Session implementing. Logout. User name displaying | https://github.com/exytab/Suzy/issues/35 | 5
3.1. | Get location on map | Get lattitude and longitude using Yandex Map API | https://github.com/exytab/Suzy/issues/11 | 20
13.1. | Yandex map to jQuery Plugin/Drag icon | Implementing Yandex API functions via jQuery Plugin | https://github.com/exytab/Suzy/issues/39 | 20
12.1. | Save location | Save geo location by clicking on map-pointer | https://github.com/exytab/Suzy/issues/28 | 10
14.1. | Show location history | Displaying all check-ins on the map | https://github.com/exytab/Suzy/issues/29 | 15
2.2. | Bussines objects (DAO) | Implementing BO for DB tables | https://github.com/exytab/Suzy/issues/32 | 15

## Sprint 3
ID | Name | Description | Sprint | Story points | Total for Sprint
4 | Pofile information | Editing personal information | Milestone 0.3 | 10 | 100
5 | Avatar | User can add-delete-change avatar |  | 15
6 | Follow | Add users to personal Followings list (page) |  | 10
7 | Unfollow | Delete user from personal Followings list
8 | Followers | See who is fillowing you |  | 10
9 | Followings on map | See all personal Followings on map |  | 25
16 | Followings list | User can observe all his ollowings. Following is a person that is followed by current user. |  | 10
15 | Error logger | Logging and saving to the file all errors, exceptions, warnings. During using the system this Logger element of system helps developers and Administrator to track errors and bugs to make the system better |  | 20
ID.Task ID | Name | Description | Link | Story points
4.1. | Profile | Implementing "profile" page for sign-up users | https://github.com/exytab/Suzy/issues/27 | 5
4.2. | Settings | "profile" page specification (inputs for Name, password, avatar) | https://github.com/exytab/Suzy/issues/26 | 5
5.1. | Upload avatar | Avatar choosing and upload, saving in DB | https://github.com/exytab/Suzy/issues/33 | 15
7.1. | Unfollow | Add / Delete users to personal Followings list (page) | https://github.com/exytab/Suzy/issues/36 | 5
6.1. | Follow |  |  | 5
9.1. | Following on map | See all personal Followings on map | https://github.com/exytab/Suzy/issues/40 | 25
15.1. | Logger | Logging and saving to the file all errors, exceptions, warnings. | https://github.com/exytab/Suzy/issues/17 | 20
8.1. | Followers | Page and logic for Followers of user | https://github.com/exytab/Suzy/issues/36 | 10
16.1. | Followings list | Page and logic for Followings of user |  | 10

## Sprint 4
ID | Name | Description | Sprint | Story points | Total for Sprint
11 | Mobile version | Using system on mobile phone | Milestone 0.4 | 60 | 100
17 | Bugs fixing | Final testing |  | 40
ID.Task ID | Name | Description | Link | Story points
11.1. | Mobile view | Optimize Suzy for mobile browsers | https://github.com/exytab/Suzy/issues/43 | 30
11.2. | API | Make Suzy other servie friendly | https://github.com/exytab/Suzy/issues/45 | 30
17.1. | Bug with avatar | Avatar did not load | https://github.com/exytab/Suzy/issues/48 | 20
17.2. | Bug with actual page | Only HOME is actual | https://github.com/exytab/Suzy/issues/47 | 10
17.3. | Bug with Follow-Following buttons | Missplaced button text | https://github.com/exytab/Suzy/issues/46 | 10